## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As a user, I want to be able to create an account, so that the app can record me and my data. | Product Owner | High | 8 | TO DO | Dod
2 | As a registered user, I want to securely log into my account,So that my information can only be accessed by me | Product Owner | High | 3 | TO DO | Dod
3 | As a user, I want to be able to view the list of yoga teachers on the homepage, so that I can find the teachers that interest me. | Product Owner | High | 8 | TO DO | Dod
4 | As a user, I want to be able to search for teachers by name or keyword, so that I can quickly find the teacher I need. | Product Owner | High | 3 | TO DO | Dod
5 | As a user, I want to be able to click on any teacher's name, so that I can view their detailed information. | Product Owner | High | 11 | TO DO | Dod
6 | As a user, I want to be able to view a teacher's age, so that I can understand their background. | Product Owner | High | 3 | TO DO | Dod
7 | As a user, I want to be able to view a teacher's introduction, so that I can understand their areas of expertise and teaching style. | Product Owner | High | 3 | TO DO | Dod
8 | As a user, I want to be able to view a teacher's work experience and years as a yoga teacher, so that I can understand their qualifications and experience. | Product Owner | High | 3 | TO DO | Dod
9 | As a user, I want to be able to add teachers to my favorites, so that I can quickly find my favorite teachers. | Product Owner | Medium | 3 | TO DO | Dod
10 | As a user, I want to be able to rate teachers or leave comments, so that I can share my experiences and opinions with other users. | Product Owner | Medium | 5 | TO DO | Dod
50
Dod
Functional tests (based on ACs) passed
Code refactor(when needed)
Code peer-reviewed
Regression tests passed
Unit tests passed (code coverage 70%)
Approved by product owner

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a user, I want to be able to create an account, so that the app can record me and my data. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | As a registered user, I want to securely log into my account,So that my information can only be accessed by me | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a user, I want to be able to view the list of yoga teachers on the homepage, so that I can find the teachers that interest me. | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a user, I want to be able to search for teachers by name or keyword, so that I can quickly find the teacher I need. | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As a user, I want to be able to view a teacher's age, so that I can understand their background. | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a user, I want to be able to view a teacher's introduction, so that I can understand their areas of expertise and teaching style. | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a user, I want to be able to view a teacher's work experience and years as a yoga teacher, so that I can understand their qualifications and experience. | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a user, I want to be able to add teachers to my favorites, so that I can quickly find my favorite teachers. | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As a user, I want to be able to rate teachers or leave comments, so that I can share my experiences and opinions with other users. | #N/A | #N/A | #N/A | #N/A | #N/A
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!