## BurnDown
Sprints | Days | Ideal Burndown | Remaining effort | PBIs completed at that day
Before the start | 0 | 80 | 80
Sprint 1 | 1 | 78 | 80
| 2 | 76 | 80
| 3 | 74 | 80
| 4 | 72 | 80
| 5 | 70 | 80
| 6 | 68 | 80
| 7 | 66 | 80
| 8 | 64 | 80
| 9 | 62 | 80
| 10 | 60 | 69 | PBI 1 & 2
Sprint 2 | 11 | 58 | 69
| 12 | 56 | 69
| 13 | 54 | 69
| 14 | 52 | 69
| 15 | 50 | 69
| 16 | 48 | 69
| 17 | 46 | 69
| 18 | 44 | 69
| 19 | 42 | 69
| 20 | 40 | 51 | PBI 3 & 4
Sprint 3 | 21 | 38 | 51
| 22 | 36 | 51
| 23 | 34 | 51
| 24 | 32 | 51
| 25 | 30 | 51
| 26 | 28 | 51
| 27 | 26 | 51
| 28 | 24 | 51
| 29 | 22 | 51
| 30 | 20 | 51
Sprint 4 | 31 | 18 | 51
| 32 | 16 | 51
| 33 | 14 | 51
| 34 | 12 | 51
| 35 | 10 | 51
| 36 | 8 | 51
| 37 | 6 | 51
| 38 | 4 | 51
| 39 | 2 | 51
| 40 | 0 | 51

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!