## Product Backlog
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | As a user, I want to find options for the Mind, Body, and Focus training programs on the home page, so that I can choose the program that interests me. | 6.1 | Create a homepage | Khaled Haji | X
|  | 6.2 | Create home class | Van Pham | X
|  | 6.3 | Design interfaces | Van Pham | X
|  | 6.4 | Integration appsync into git repository | Van Pham, Khaled Haji | X
|  | 6.5 | Unit tests passed (code coverage 70%) | Kaida Zhang, Brian | X
|  | 6.6 | Code peer-reviewed | Kaida Zhang, Brian | X
4 | As a user, I want to see various yoga poses within a selected training program, so that I can choose the poses that suit me for practice. | 10.1 | Create yoga page | Kimberley Tan | X
|  | 10.2 | Create database | Van Pham | X
|  | 10.3 | verify permissions | Van Pham | X
|  | 10.4 | Design interfaces | Van Pham | X
|  | 10.5 | Unit tests passed (code coverage 70%) | Kaida Zhang, Brian | X
|  | 10.6 | Integration appsync into git repository | Kimberley Tan, Van Pham | X
|  | 10.7 | Code peer-reviewed | Kaida Zhang, Brian | X

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a user, I want to find options for the Mind, Body, and Focus training programs on the home page, so that I can choose the program that interests me. | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | As a user, I want to see various yoga poses within a selected training program, so that I can choose the poses that suit me for practice. | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A